## Risk Treatment Plan
Risk ID | Risk Level | Treatment Decision | Remediation Action | Owner | Due Date | Status
R-001 | High | Mitigate | Enforce phishing-resistant MFA (FIDO2/passkeys) for all Entra ID accounts and run quarterly phishing-simulation training. | Security Engineering | 2026-11-06 | In Progress
R-002 | High | Mitigate | Implement just-in-time privileged access and session recording for all PAM vault checkouts. | Security Engineering | 2026-11-21 | Open
R-003 | High | Mitigate | Deploy immutable, air-gapped backups for the customer database and test restoration quarterly. | IT Infrastructure | 2026-11-21 | Open
R-004 | High | Mitigate | Segment the Core Banking / Loan Origination System from general network access and enable endpoint detection on all hosts touching it. | IT Infrastructure | 2026-12-06 | Open
R-005 | High | Mitigate | Require SOC 2 reports and conduct annual security assessments for all vendors with data access. | Vendor Risk Management | 2026-12-21 | Open
R-008 | High | Mitigate | Implement dual-approval for wire transfers above a defined threshold and deploy email authentication (DMARC enforcement). | Finance / IT Security | 2026-10-22 | In Progress
R-009 | High | Mitigate | Enforce automated patch management with a 14-day SLA for critical vulnerabilities on all endpoints. | IT - Endpoint Management | 2026-11-06 | Open
R-010 | High | Mitigate | Automate deprovisioning to revoke access within 24 hours of an HR-reported termination event. | IT - Identity & Access | 2026-10-22 | Not Started
R-013 | High | Mitigate | Publish an approved AI tool list and deploy a data-loss-prevention policy blocking sensitive data from unapproved AI endpoints. | Compliance / IT Security | 2026-11-21 | Not Started
R-006 | Medium | Mitigate | Implement automated cloud configuration scanning (CSPM) with alerts on public-facing database exposure. | Security Engineering | 2026-11-06 | Open
R-007 | Medium | Mitigate | Deploy data-loss-prevention monitoring on data exports from the customer database and source code repository. | Security Operations | 2026-11-21 | Not Started
R-014 | Medium | Mitigate | Implement automated segregation-of-duties monitoring within the Loan Origination System to flag conflicting entitlements. | IAM Governance | 2026-11-21 | Not Started

## Legend & Notes
Risk Treatment Plan — Legend & Notes
Purpose: Documents the remediation decision, specific action, accountable owner, and target date for every High or Critical risk identified in Risk-Register.xlsx.
Scope: Only High and Critical risks receive a formal treatment plan entry. Medium risks with a Mitigate decision are included selectively where a concrete control improvement was identified; Low risks and risks marked Accept or Transfer in the Risk Register are not tracked here.
Column definitions:
Risk ID — Cross-reference to Risk-Register.xlsx.
Risk Level — Carried over from the Risk Register at the time this plan was created.
Treatment Decision — Avoid, Mitigate, Transfer, or Accept.
Remediation Action — The specific control or process improvement being implemented.
Owner — The role or team accountable for completing the remediation (not a named individual, since this is a simulated environment).
Due Date — Target completion date, set relative to the plan's creation date.
Status — Not Started, Open, In Progress, Complete, or Overdue.
Note: Apex Financial Services is a fictional company created for portfolio purposes. All risks, owners, and dates in this file are simulated and do not represent any real organization.